PROJECT PLANNING NOTES FOR LARGE CLUB RANGE BUILDINGS

These notes are intended to assist sports clubs and other similar organisations who are considering the purchase of a Passmore Club Range building.

Passmores is a sectional timber buildings manufacturer.  Our role is that of specialist supplier, with responsibility for the design, manufacture and erection of the timber superstructure.

Unless you have the necessary expertise amongst the membership of your organisation, we recommend that a local builder is appointed to construct the foundation and to undertake the role of main contractor.  He will be able to provide the limited amount of project management needed and is likely to be able to supply those trades not available through Passmores.

PERMISSION. Before starting work Town and Country Planning Permission and Building Regulations approval should be obtained.It is usual practice to obtain Planning Permission first, followed by Building Regulations approval.  The responsibility for obtaining approvals rests with the customer and if you decide to proceed without approval, you will be doing so at your own risk.

The government website www.planningportal.gov.uk contains a wealth of useful information about planning procedures and costs. You can make an application online, monitor its progress and also download customised block and site plans to support your application.

DRAWINGS. Individually prepared drawings are available from Passmores to accompany your Planning and Building Regulations applications. The cost of drawings will be refunded at the time you order the building. To assist customers we supply detailed guidance notes with every drawing.

FOUNDATION.  Passmores supply a separate dimensioned baseworks drawing which will be sent out at time of order acknowledgement.

The foundation should be prepared well ahead of the scheduled delivery date to allow for curing, dimensional checking and any rectification work. Below ground drainage works are usually undertaken in conjunction with the foundation.

In most cases, foundation trench depth and width is agreed on site between the Approved Inspector and the baseworks contractor.  If ground conditions are poor you may be asked to provide an engineer’s design and this is best obtained from a local structural engineer or architect. Please do not adopt an alternative foundation design without reference to Passmores as it may not suit the building ordered.

RUNNING ORDER.  A programme of work is provided at time of order acknowledgement and the running order is generally as detailed in the paragraphs below.

ERECTION OF BUILDING SHELL. This takes place in 2 stages.  Initially Passmores will erect and anchor down the external wall panels and structural partitions.  We will need lorry access within 20m of the base and 240 volt electricity.  If the site is open to the public we recommend that it is enclosed with temporary site fencing, to be erected by the main contractor. Passmores will return to install the roof structure after erection of scaffolding.

SCAFFOLDING. After erection of the walls and structural partitions, we require scaffolding so that the roof structure can be safely installed.  A dimensioned drawing of the required scaffolding is included with the order acknowledgement folder.  (We can quote for scaffolding upon request but the least cost route is usually a local scaffolding company known to your groundworks contractor).

WEATHERING OF THE ROOF. This will usually be either 2 layer hot bonded felt or fibre cement slates.

ELECTRICAL, HEATING AND PLUMBING 1ST FIX. This deals with the installation of wiring and pipe runs and the fixing of support noggins for fittings and is carried out by your appointed contractors prior to internal lining.

INSULATION AND DRY LINING. If carried out by Passmores, the interior work will be undertaken in the following order:

- Installation of insulated floor

- Installation of insulation and plasterboard to ceiling

- Erection on non-structural partitions and internal door sets

- Installation of insulation to external walls

- Installation of plasterboard to external walls and both sides of partitions

- Jointing, taping and rubbing down of plasterboard joints

- Fitting of skirting board, internal door architraves and window boards

- This completes Passmores contract

ELECTRICAL, HEATING AND PLUMBING 2ND FIX. This deals with the installation of fittings and their connection to wiring and plumbing runs previously installed and is carried out by your appointed contractors.

DECORATION AND AND FLOOR COVERING. The rubbing down process for plasterboard joints creates a lot of dust and we recommend that the interior is thoroughly cleaned prior to decoration and installation of the floor covering.  If thin carpet or vinyl floor covering is to be specified, we recommend that your floor contractor overlays the chipboard with 4mm plywood with staggered joints (this is to prevent joint show through).

KEY DATES AND PROJECT BUDGETING. The checklist overleaf may be of assistance in planning the project time scale and providing budget guidelines.

Please contact Passmores if you require any information or assistance

| Passmores Portable Buildings Limited 01634 290033 | Doc. 636 © Passmores 11/07 Revised 06/15 Information Sheet 23 |
| --- | --- |

Checklist – Key Dates and Project Budgeting

| Item | Key dates |  |  |  | Estimate of cost |
| --- | --- | --- | --- | --- | --- |
| Planning Permission | Application submitted |  |  | Application cost | £ |
|  | Approval received |  |  |  |  |
| Building Regulations | Application submitted |  |  | Application cost | £ |
|  | Approval received |  |  |  |  |
| Foundation | Quotations requested |  |  |  |  |
|  | Main contractor appointed |  |  | Foundation cost | £ |
|  | Foundation start date |  |  |  |  |
|  | Foundation finish date |  |  |  |  |
| Building | Building ordered |  |  | Building cost | £ |
|  | Erection of walls |  |  |  |  |
|  | Scaffolding |  |  | Scaffolding cost | £ |
|  | Installation of roof |  |  |  |  |
|  | Roof covering |  |  | Roof costs * | £ |
| Sub - trades | Electrical contractor appointed |  |  | Electrical costs | £ |
|  | Plumbing contractor appointed |  |  | Plumbing costs | £ |
|  | 1st fix start date |  |  |  |  |
|  | Insulation & dry lining start date |  |  | Insulation & dry lining costs * | £ |
|  | 2nd fix start date |  |  |  |  |
|  | Decoration & floor covering start date |  |  | Decoration costs | £ |
|  | Internal fixtures and fittings |  |  | Fitting out costs | £ |
|  |  |  |  | TOTAL | £ |
| *If not quoted by Passmores |  |  |  |  |  |